## Timeline
Phase | Task | Expected outputs (milestones in blue) | Responsibility | Status | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb
[5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Phase 1: Preparatory phase
Preparations | FSA 2021 lessons learnt sessions (internal, external) | 1-day workshop and lessons learnt report | WFP (VAM and Comms?) | In progress | Jun W2: 15/6
| Draft contract CSO (data sharing) | Final contract signed by CSO and WFP | WFP (VAM Officer 2) | bar: Jun W4
| Developing Scope of Work for FSA 2022 | Scope of Work document in English and Arabic | WFP | bar: Jun W4 to Jul W1
Staff capacity | Recruitment of TDY Business Support/translation/IT staff for FSA 2022 | 1-2 CO programme/IT staff officially seconded to support the FSA full time or part time | WFP ((VAM Officer 1) | bar: Aug W1 to Dec W4
Enumerators | Update enumerator list based on performance review from FSA 2021 data collection | Clean 2021 Excel file with updated contact details of approved enumerators | WFP (VAM Officer 4) | Finalised | bar: May W1
| CSO share final list of new enumerators with WFP | One Excel files with contact details of proposed enumerators | CSO | bar: Jul W1
| WFP enumerator selection | One Excel file with new cohort of UN enumerators (check WFP VAM/M&E recruitment roster) Finalise enumerator database | WFP (VAM Officer 1 and 4) | bar: Jul W4 to Aug W1
Tool | Revision of tool based on lessons learnt from FSA 2021 | Near-final tool | WFP (VAM Officer 2) | bar: Jun W4 to Jul W1
| Sharing of near-final tool with CSO for endorsement | Final, endorsed tool | WFP (VAM Officer 1) | bar: Jul W4
| Share final tool with CO for update on xls form | Final xls form | WFP (VAM Officer 5) | bar: Aug W1 to Aug W2
| Revision of training manual (check manuals from other COs) | Final training manual | WFP (VAM Officer 1) | bar: Aug W1 to Aug W4
| Update training presentations | Final training presentations | WFP (VAM Officer 6) | bar: Aug W3 to Aug W4
Sampling | Agreement with CSO on sampling approach (add sample for information on IDPs in camps) |  | WFP/CSO (VAM Officer 3) | bar: Sep W1 to Sep W2
| Selection of enumeration areas and villages |  | WFP/CSO (VAM Officer 3) | bar: Sep W1 to Sep W2
| Sample completed and shared with CSO for endorsement + stamp | Final, endorsed sampling list of clusters to be sampled in all districts | WFP/CSO (VAM Officer 3) | bar: Sep W1 to Sep W2
Official agreements with authorities | FSA 2022 kick off meeting with government (review of government structure based on the funding limitations) | 1-day meeting | WFP (VAM Officer 1) | bar: Jul W3
| Endorsement and stamp of training manual | Final endorsed and stamped training manual | CSO | bar: Jul W4
| CSO share list of members to different committees (supreme, survey, operation room, governorate supervisors) | Final agreed list with all committee members | CSO | bar: Aug W2
Recruitment and contracting for TPSP for admin/logistics | EOI for TPSP and evaluation | Final list of companies to share proposal with | WFP (VAM Officer 3) | In progress | bar: May W3; Aug W1 to Aug W2
| Call for proposals for TPSP |  | WFP (VAM Officer 2)
| Evaluation and contracting of TPSP | Final signed agreement with selected TPSP | WFP (VAM Officer 2) | bar: Aug W3
| Share letter with CSO to inform the selected TPSP and the ToR |  | WFP (VAM Officer 1) | bar: Aug W3
| Establish initial governorate/district-level communication to facilitate easier movement for enumerators during data collection | Communication shared with all relevant governorate/district-level authorities with SOW of FSA, planned dates of data collection, informing about tablet etc. | TPSP | bar: Aug W3
Recruitment and contracting for TPM company | Call for proposals for TPM |  | WFP (VAM Officer 2)
| Evaluation and contracting of TPM | Final signed agreement with selected TPM | WFP (VAM Officer 2) | bar: Sep W3
| Share letter with CSO to inform the selected TPM and the ToR |  | WFP (VAM Officer 1) | bar: Sep W3
Procurement | Procure 500 tablets | 500 tablets physically in Aden | TPSP | bar: Sep W1
Phase 2: Training and field deployment planning
TOT | Selection of trainers/trainees for TOT | Final list with trainers/trainees | WFP (VAM Officer 1) | bar: Sep W1
| Update training agenda | Final agenda for TOT | WFP (VAM Officer 1) | bar: Sep W2
| Booking of venue | Booking confirmation | TPSP | bar: Sep W1
| Facilitate logistics of trainers and trainees |  | TPSP | bar: Sep W1
| Update tablets with final version of questionnaire | 70 tablets available for training with updated questionnaire | TPSP | bar: Sep W1
| 1-day information meeting with all committee members to present survey plan & roles | 1 day official meeting the day before the TOT | WFP (VAM Officer 1) | bar: Sep W3
| TOT Training (include also committee members and operation room) | 5-day training | WFP (VAM Officer 1) | bar: Sep W3
| Training of CSO/government technical staff on key food security indicators | Key CSO staff to be included in the TOT | WFP (VAM Officer 1) | bar: Sep W3
TPSP recruiting enumerators | Confirmed list of final enumerators based on availability for field data collection | Final list with names and contact details | TPSP | bar: Aug W4
| Contracting of enumerators | Individual contracts signed with all enumerators prior to leaving to the field | TPSP | bar: Oct W1 to Oct W2
Enumerators Training | Booking of venue | Booking confirmation | TPSP | bar: Sep W1
| Facilitate logistics of trainers and trainees |  | TPSP
| Enumerator training - batch 1 | 6-day training (start of training on Tuesday, test on Thursday, selection of final enumerators Thursday evening, communication to district level authorities Friday, finalise training Saturday to Monday, travel to the field on Tuesday) | WFP (VAM Officer 1) | bar: Sep W4 to Oct W1
| Enumerator training - batch 2 | 6-day training | WFP (VAM Officer 1) | bar: Oct W1 to Oct W2
Field preparations | Overall district field implementation plan finalised and submitted for approval | Generic field implementation plan finalised with information about how to best divide the districts, suggested optimal team sizes per enumeration area | TPSP (with WFP approval) | bar: Sep W4 to Oct W1
| List of vehicles and enumerator IDs for each district to be shared with CSO and governorate-level authorities for approval | Final approvals | TPSP | bar: Sep W4 to Oct W1
| Orienting and starting operation room | Operation room reestablished at CSO premises and briefing for members from WFP has been conducted | WFP (VAM Officer 1) | bar: Sep W4 to Oct W1
Finalizing monitoring plan, indicators and reporting with TPM | Approval of TPM monitoring plan, indicators and frequency of reporting | Final monitoring form | WFP (VAM Officer 2) | bar: Sep W4
| Final reporting format cleared by WFP | Final written agreement with requirements | WFP (VAM Officer 2) | bar: Oct W1
Phase 3: Data collection, field checks
| Data collection - batch 1 |  | TPSP | bar: Oct W2 to Nov W1
| Data collection - batch 2 |  | TPSP | bar: Oct W3 to Nov W3
| Perdiodic data downloads/high frequency data quality checks/feedback to the field through the operation room | Saved versions of encrypted raw datasets for CSO | WFP (VAM Officer 5) | bar: Oct W2 to Nov W3
| TPM visits |  | TPM | bar: Oct W2 to Nov W3
| WFP monitoring visits |  | WFP | bar: Oct W2 to Nov W1
| End of field work | Download of final raw dataset | WFP (VAM Officer 5) | bar: Nov W4
| Final report from operation room | Final report | Operation room | bar: Nov W4
Phase 4: Data cleaning and analysis
Data cleaning | Data cleaning | Final syntax with all data cleaning steps | WFP (VAM Officer 2)/CSO | bar: Dec W1 to Jan W1
Analysis | Computation of the key food security indicators |  | WFP (VAM Officer 2) | bar: Dec W4 to Jan W2
| Fill in matrix with FSA results for IPC analysis | Final matrix | WFP (VAM Officer 2) | bar: Jan W1 to Jan W2
| Additional vulnerability analysis to support IPC analysis |  | WFP (VAM Officer 2) | bar: Jan W2 to Jan W4
Phase 5: IPC analysis/FSA report
IPC analysis workshop | Co-facilitate the IPC analysis | Final acute food insecurity figures | FAO lead | bar: Jan W3 to Jan W4
IPC reports | Contribute to final IPC communication products | Final Key Messages and Acute Food Insecurity Report | WFP (VAM Officer 1 and 2) | bar: Feb W1 to Feb W4
FSA 2022 report | Analyse all FSA data | Final FSA report | External