## CO MMR_DE _RB 2nd review (CO)
Recommendations of the Decentralized Evaluation of WFP’s Relief Food and Cash Assistance to Conflict-Affected People in Kachin and Northern Shan, Myanmar (2016-2019): Management Response from WFP Myanmar Country Office
Rec. # | Recommendation [as per evaluation report] | Management Response [Is recommendation Accepted, partially accepted or not accepted? If partially accepted or not accepted, provide a brief response] | Actions to be taken (Briefly state what actions will be taken to address the recommendation) | Action By [Unit/focal point in WFP Country Office] | Implementation timeframe [Month, Year] | Status [Not started/In progress/On hold/ Complete]
1 | WFP Country Office should critically review the vulnerability criteria set in 2016 and assess whether they remain relevant. While the vulnerability criteria heavily rely on one’s ability to work and assume that household members are able to find income generating opportunities, the data on livelihoods collected during the evaluation suggests that this situation varies across seasons, states and townships. WFP could propose, via the Food Security and Livelihoods cluster, to conduct a joint-labour market assessment to determine the seasonality of livelihood opportunities and bridge the gap in data. With this study, WFP could decide whether these criteria should be revised and whether the entitlements remain appropriate. | Accepted | - Conduct a Desk Review of existing vulnerability and targeting criteria; - Organize a remote one-day review workshop and update the criteria prior to the preparation of Field Level Agreements with Cooperating Partners. | Research, Assessment and Monitoring (RAM) Unit | Oct-Dec 2020 | Not started
|  |  | Conduct a joint labour market assessment with the Food Security and Livelihoods cluster once Covid-19 situation allows. | RAM Unit | As soon as COVID-19 situation allows in late 2020/early 2021 | Not started
2 | WFP Country Office should strengthen the Complaint and Feedback Mechanism (CFM) to handle all complaints in a timely manner and contribute to improving the programmatic orientation of relief activities. A significant volume of beneficiaries’ complaints are provided orally to Cooperating Partner staff and there is no process in place to ensure that these complaints are registered at the WFP level. WFP Sub-Offices should aim to increase the usage of formal channels by (i) setting up a toll-free hotline, (ii) increasing the frequency of collecting feedback from the complaint boxes to two times a month, (iii) developing a format for complaints to help recipients provide all the required information for treatment, and (iv) clarifying the role of the Food Management Committee/Camp Management Committee in handling these complaints through a Terms of Reference (ToR)/Memorandum of Understanding (MoU). WFP should systematise the recording of all complaints in a dedicated CFM tool, through the development of a detailed Standard Operating Procedure for Cooperating Partners on handling complaints, a tool for Cooperating Partners to record oral complaints. | Accepted | Develop Complaints and Feedback Mechanism (CFM) into Community Engagement Mechanism which includes information provision, participation and CFM. | Protection, Gender and Accountability to Affected Populations (AAP) Unit | 2020-06-01 | Completed
|  |  | Finalize Standard Operating Procedure for the Community Engagement Mechanism, providing for timely response (between 24 hours and 1 week depending on the priority level) and capture of beneficiary complaints provided orally to Cooperating Partner staff, and specifying the role of the Food Management Committee/Camp Management Committee in complaints handling. | Protection, Gender and AAP Unit | 2020-06-01 | Completed
|  |  | Brief Community Engagement Mechanism focal points in the Field Offices on the Community Engagement Mechanism Standard Operating Procedure | Protection, Gender and AAP Unit | 2020-06-01 | Completed
|  |  | Brief Community Engagement Mechanism focal points, as well as focal points for Protection from Sexual Exploitation and Abuse (PSEA), on the handling of sexual exploitation and abuse complaints. | Protection, Gender and AAP Unit | 2020-07-01 | Completed
|  |  | Produce and disseminate forms for beneficiaries to use with suggestion boxes, and for partners to use for receiving complaints at help desks. | Protection, Gender and AAP Unit | Jun-Oct 2020 | In progress
|  |  | Roll out Sugar Customer Relationship Management (Sugar CRM) software. | Protection, Gender and AAP Unit | Jun-Oct 2020 | In progress
|  |  | Set up toll-free hotlines. | Protection, Gender and AAP Unit | Jun-Dec 2020 | In progress
|  |  | Prepare updated Terms of Reference for Food Management Committees which include detail on how Food Management Committees may contribute towards complaints handling (see Recommendation 7 for more information). | Protection, Gender and AAP Unit | Aug-Oct 2020 | In progress
|  |  | Brief Cooperating Partners on the Community Engagement Mechanism and implement tracking sheets to ensure oral complaints are captured and fed into the Sugar Customer Relationship Management (Sugar CRM) tool, with collection of feedback from suggestion boxes two times a month. | Protection, Gender and AAP Unit | Oct-Dec 2020 | Not started
3 | Review the rules of inclusion/exclusion for programme recipients who travel outside of the camps. WFP should critically review these rules and provide Internally Displaced People (IDPs) with more flexibility, while also ensuring sufficient monitoring to avoid aid diversion. Therefore, WFP could consider a quarterly registration of beneficiaries instead of monthly registration. This decrease in the frequency of registration may also decrease the workload of Cooperating Partners, as the process was reportedly time-consuming. | Accepted | - Review the rules of the inclusion/exclusion procedure based on the livelihood context and conflict situation. - Review the efficiency (time management) of conducting a quarterly registration of beneficiaries. - Conduct monthly/quarterly monitoring by Field Office staff, based on the accessibility and remoteness of the distribution sites. | Kachin Field Office | Oct-Dec 2020 | Not started
4 | Design a Standard Operation Procedure for the monthly beneficiary lists update. As the process's lack of clarity has led recipients to stop leaving the camps to search for livelihood opportunities, WFP Sub-Offices should establish a clear set of rules and widely communicate them to all WFP partners and beneficiaries, for example through group meetings and posters. | Accepted | - Draft Standard Operation Procedures for updating beneficiary lists in Kachin and Shan to be reviewed and agreed at a workshop. - Organize an effective coordination mechanism for updating beneficiary lists and communicating these with partners and beneficiaries. | Relief Unit | Oct-Dec 2020 | Not started
5 | Revise the Standard Operation Procedure for Post-Distribution Monitoring (PDM) on relief activities. In order to limit bias, WFP should (i) collect data twice a year or at minimum during the lean period and (ii) ensure data collection occurs three weeks after the distribution. | Accepted | - Revise the SOP for PDM to cover the lean and peak seasons. - Coordinate with the Field Offices to ensure PDM data collection occurs two to three weeks after the distribution. | RAM Unit | 2020-09-01 | In progress; Remote monitoring/PDM has taken place in April and June 2020 to cover the peak hunger seasons prior to harvesting.
6 | WFP Country Office could play a more significant role in IDPs' return process. In areas protection actors consider safe, WFP Country Office could increase the return package to one year to cover a full agricultural production cycle and thus reinforce livelihood restoration. In these areas WFP could further increase linkages with Strategic Outcome 2 and proposed livelihood activities. As WFP is already involved in the Protection Working Group (PWG), WFP Sub-Offices could contribute to implementing the PWG operational guidance by: (i) continuously providing monthly support for those IDPs in camps who start a step-by-step return, (ii) facilitating local integration and coordination with livelihood actors, (iii) planing for the potential extension of the support according to the level of harvest, and (iv) organising different types of support according to the level of safety of the places assessed (e.g. school feeding). | Partially Accepted (WFP Country Office fully endorses the importance of playing a full role in the IDP return process. However, the durable solutions required go far beyond WFP’s own mandate – indeed, the Resident Coordinator's Office is in the process of establishing a Durable Solutions Unit to coordinate all activities in support of IDP returns. WFP retains strong reservations on the provision of a one-year return ration – a more targeted period to encourage a return before planting season may be more appropriate, combined with follow-up support to livelihood activities. In this respect, WFP may consider a one-off livelihood cash transfer, which would address the challenge of accessing beneficiaries in multiple small clusters in remote locations. This could be accompanied by relevant training. This kind of intervention would give the returnees dignity and a certain status in their communities as people who are returning with capital to invest in livelihoods and stimulate the local economy. This and other options will be discussed further in the review workshop planned in response to this recommendation.) | Organize a review workshop to set a common response strategy for returning IDPs in Kachin and Shan. | Head of Programme/Deputy Country Director | Oct-Dec 2020 | Not started
7 | WFP Country Office should clarify and then officialise the role and responsibilities of the Food Management Committees (FMC) in coordination with Camp Management Committees (CMC). In turn, it will contribute to increasing women's role in community-level decision-making. While women are well represented in FMCs, FMCs' role decreased over time in favour of CMCs e.g. for the monthly update of beneficiary lists. Key to that problem stems from the fact that the expected roles and responsibilities of FMCs are not clearly defined. | Accepted | Prepare Terms of Reference for FMCs and Project Management Committees with emphasis on women’s participation and leadership. | Protection, Gender and AAP Unit | Aug-Oct 2020 | In progress
|  |  | Incorporate information in local languages on the role of FMCs in key messages for beneficiaries at distribution points. | Protection, Gender and AAP Unit | Sep-Nov 2020 | Not started
|  |  | Provide Training of Trainers for Cooperating Partners to roll out refresher trainings for FMCs and CMCs so all are clear on their role. | Protection, Gender and AAP Unit | Nov 2020-Apr 2021 | Not started
|  |  | Instruct Cooperating Partners to work with FMCs to update beneficiary lists. | Protection, Gender and AAP Unit | 2020-12-01 | Not started

## CO MMR_DE _RB 2nd review (hidden)
Management Response from WFP Myanmar Country Office to the recommendations of the decentralized evaluation of WFP’s relief food and cash assistance to conflict-affected people in Kachin and Northern Shan, Myanmar
from 2016 to 2019
Rec. # | Recommendation [as per evaluation report] | Management Response [Is recommendation Accepted, partially accepted or not accepted? If partially accepted or not accepted, provide a brief response] | Actions to be taken (Briefly state what actions will be taken to address the recommendation) | Action By [WFP Country Office, WFP Regional Bureau, WFP Headquarters, External Stakeholders (UN Agency, Government body, Donor)] | Implementation timeframe [Month, Year] | Status [Not started/In progress/On hold/ Complete] | For RB comments
1 | WFP CO should critically review the vulnerability criteria set in 2016 and assess whether they remain relevant. While the vulnerability criteria heavily rely on one’s ability work and assume that household members are able to find income generating opportunities, the data on livelihoods collected during the evaluation suggests that this situation varies across seasons, states and townships. WFP could propose, via the Food Security and Livelihoods cluster, to conduct a joint-labour market assessment to determine the seasonality of livelihood opportunities and bridge the gap in data. With this study, WFP could decide whether these criteria should be revised and whether the entitlements remain appropriate. | Accepted | - Review and update the vulnerability and targeting criteria (including inclusion and exclusion criteria) based on available information. - Organize a remote one day workshop and update the criteria for Kachin and Shan prior to the next Field Level Agreement preparation. - Conduct a joint-labour market assessment with food security and livelihood cluster once Covid-19 situation allows. | Marie Enlund, RAM unit | 2020-10-01 | In progress
2 | WFP CO should strengthen the Spell out (CFM) to handle all complaints in a timely manner and contribute to improving the programmatic orientation of relief activities.[1] A significant volume of beneficiaries’ complaints are provided orally to Spell out (CP) staff and there is no process in place to ensure that these complaints are registered at the WFP level. WFP Spell out (SO) should aim to increase the usage of formal channels by (i) setting up a toll-free hotline, (ii) increasing the frequency of collecting feedback from the complaint boxes to 2 times a month, (iii) developing a format for complaints to help recipients provide all the required information for treatment, and (iv) clarifying the role of the Spell out (FMC/CMC) in handling these complaints through a ToR/Memorandum of Understanding (MoU). WFP should systematise the recording of all complaints in a dedicated CFM tool, through the development of a detailed Standard Operating Procedures (SOPs) for CPs on handling complaints a tool for CPs to record oral complaints. | Accepted | - Produce and disseminate complaints forms for suggestion boxes and forms for receiving complaints to helpline (in progress) - Brief Cooperating Partners on the Spell out (CEM) and implement with them tracking sheets for help desks, and collection of feedback from suggestion boxes 2 times a month - Set up toll-free hotlines (negotiations with telecommunications providers in progress) Roll out Sugar CRM software (configuration in progress) | Michelle Sanson, Protection Gender and AAP Unit | 2020-06-01 | In progress
|  |  | Rename Complaints and Feedback Mechanism into Community Engagement Mechanism which includes information provision, participation and CFM (completed) | Protection Gender and AAP Unit | By when? | Completed
|  |  | Finalize Standard Operating Procedure for the CEM providing for timely response (between 24 hours and 1 week depending on the priority level) and capture of beneficiary complaints provided orally to CP staff and specification of role of FMC/CMCs in complaints handling (completed) | Protection Gender and AAP Unit | By when? | Completed
|  |  | Brief CEM focal points in the field offices regarding the CEM Standard Operating Procedure (completed) | Protection Gender and AAP Unit | By when? | Completed
|  |  | Brief CEM focal points plus focal points for protection from sexual exploitation and abuse (PSEA) regarding handling of SEA complaints | Protection Gender and AAP Unit | By when? | Completed
3 | Review the rules of inclusion/exclusion for programme recipients who travel outside of the camps. WFP should critically review these rules and provide IDPs with more flexibility, while also ensuring sufficient monitoring to avoid aid diversion. Therefore, WFP could consider a quarterly registration of beneficiaries. This decrease in the frequency of registration may also decrease the workload of CPs, as the process was reportedly time-consuming. | Accepted | - Review the rules of inclusion/exclusion procedure based on the livelihood context and conflict situation. - Review the efficiency( time management) for conducting quarterly registration of beneficiaries. - Conduct frequent monitoring by field office staff to avoid assistance diversion. | Ja Seng, Head of Kachin field office | 2020-10-01 | In progress
4 | Design a Spell out (SOP) regarding the monthly beneficiary lists update. As the process’ lack of clarity has led recipients to stop leaving the camps to search for livelihood opportunities, WFP SO should establish a clear set of rules and widely communicate them to all WFP partners and beneficiaries, for example through group meetings and posters. | Accepted | - Organize a review workshop and set common agreement on beneficiaries updating SOP for Kachin and Shan. - Organize effective coordination mechanism to set the rules and communication with partners and beneficiaries. | Soi Lang Seng, Relief Unit | By when? December 2020?,2020 | In progress
5 | Revise the Spell out (SOP) for Spell out (PDM) on relief activities. In order to limit the bias, WFP should (i) collect data twice a year or at minimum during the lean period and (ii) ensure data collection occurs 3 weeks after the distribution. | Accepted | - Conduct two Spell Out (PDM)s to cover for lean and peak seasons - Ensure PDM data collection occurs 2 to 3 weeks after the distribution | T Nang Seng Pan, RAM unit | 2020-10-01 | In progress | - Conduct two relief PDM (TBD) For the upcoming PDM to be conducted in October 2020, it will be ensured that the exercise takes place within 2 to 3 weeks after the distribution. In 2020, in light of Covid-19 context, PDM shifted to remote monitoring, and has taken place twice: once in April, and once in July, the periods of which should cover the peak hunger season prior to harvesting. Conducting two PDMs to cover for lean and peak seasons will be ensured going forward. - Ensure PDM data collection occurs 3 weeks after the distribution
6 | WFP CO could play a more significant role in the Internally Displaced People (IDP)s’ return process. In areas protection actors consider safe, WFP CO could increase the return package to 1 year to cover a full agricultural production cycle and thus reinforce livelihood restoration. In these areas WFP could further increase linkages with Strategic Outcome 2 (SO2) and proposed livelihood activities. As WFP is already involved in the Protection Working Group (PWG), WFP Spell out (SO) could contribute to implementing the Spell out (PWG) operational guidance by: (i) continuously providing monthly support for those IDPs in camps who start a step-by-step return, (ii) facilitate local integration and coordination with livelihood actors, (iii) plan for the potential extension of the support according to the level of harvest, and (iv) organise different types of support according to level of safety of the places assessed (e.g. school feeding). | Partially Accepted (The CO fully endorses the importance of playing a full role in the IDP return process. However, the durable solutions required go far beyond WFP’s own mandate – indeed, the RCO is in the process of establishing a Durable Solutions Unit to coordinate all activities in support of IDP returns. The CO retains strong reservations on the provision of a one-year return ration – a more targeted period to encourage a return before planting season may be more appropriate, combined with follow-up support to livelihood activities. In this respect, CO may consider a one-off livelihood cash transfer, which would address the challenge of accessing beneficiaries in multiple small clusters in remote locations. This could be accompanied by relevant training. This kind of intervention would give the returnees dignity and a certain status in their communities as people who are returning with capital to invest in livelihoods and stimulate the local economy. This and other options will be discussed further in the review workshop planned in response to this recommendation.) | - Organize a review workshop to set common response strategy for returning IDPs in Kachin and Shan. | Marcus Prior, Head of Programme/Deputy Country Director | By when? | In progress | - Coordinated with Myanmar government, WFP contributed cash based transfers to the PLW and children in IDP camps and in response to the COVID-19, government social protection activities.
7 | WFP CO should clarify and then officialise the role and responsibilities of the Spell out (FMC)s in coordination with Spell out (CMCs). In turn, it will contribute to increasing women’s role in community-level decision. While women are well represented in FMCs, FMCs’ role decreased over time in favour of CMCs, e.g. for the monthly update of beneficiary’s lists. Key to that problem stems from the fact that the expected role and responsibilities of FMCs are not clearly defined. | Accepted | - Prepare Terms of Reference for Food Management Committees and Project Management Committees with emphasis on women’s participation and leadership (draft in progress) - Provide Training of Trainers for Cooperating Partners to roll out refresher trainings for FMCs and CMCs so all are clear on their role (October to November) - Incorporate information in local languages on Food Management Committee role in key messages for beneficiaries at distribution points (October) - Instruct Cooperating Partners to work with FMCs to update beneficiary lists (November to December) | Michelle Sanson, Protection Gender and AAP Unit | 2020-08-01 | In progress
|  |  | Prepare Terms of Reference for Food Management Committees and Project Management Committees with emphasis on women’s participation and leadership (draft in progress) Do not include the status |  | By when? | In progress
|  |  | Provide Training of Trainers for Cooperating Partners to roll out refresher trainings for FMCs and CMCs so all are clear on their role (October to November) Do not include the status |  | 2020-11-01 | In progress
|  |  | Incorporate information in local languages on Food Management Committee (FMC) role in key messages for beneficiaries at distribution points (October) Do not include the status |  | 2020-10-01 | In progress
|  |  | Instruct Cooperating Partners to work with FMCs to update beneficiary lists (November to December) Do not include the status |  | 2020-12-01
Note on B5: KANEMITSU Yumiko: What is the action of the highlighted part in red?
Note on D5: KANEMITSU Yumiko: The red part is the status. It has to go to the status. The need to be broken down.
Note on D14: KANEMITSU Yumiko: Need to brak it down, the deadline is not matching
Note on E4: KANEMITSU Yumiko: Do not include personal name.
Note on E5: KANEMITSU Yumiko: Do not include a personal name.
Note on E10: KANEMITSU Yumiko: No personal name
Note on E11: KANEMITSU Yumiko: Same as above.
Note on E12: KANEMITSU Yumiko: Same as above.
Note on E13: KANEMITSU Yumiko: No personal name, only the functional title or function's name.
Note on E14: KANEMITSU Yumiko: No personal name
Note on F13: KANEMITSU Yumiko: Need a date.
Note on F14: KANEMITSU Yumiko: This bis not matching!